## Gantt Chart
	lanslide Triggering System				0%
	Final Assignment
	Pham Thai Quang Nguyen		Friday, March 15, 2024

										12					13					14					15					16					17					18					19					20					21					22					23					24					25					26					27					28					29					30					31					32					33					34					35					36					37
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Mar-24					Apr-24					May-24					Jun-24					Jul-24					Aug-24					Sep-24
			17-Mar-2024	32	30-Apr-2024	0%	45			17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13
	Data warehouse construction	PostgreSQL	17-Mar-2024	9	28-Mar-2024	0%	12	0	20
	Database schema design		17-Mar-2024	5	21-Mar-2024		5	0	5
	normalization					0%	5	0	5
	Writing DDL script		17-Mar-2024	10	28-Mar-2024	0%	12	0	10
	Updating Triggering
	Milestone 1

	Collecting pipeline	Apache Airflow	23-Mar-2024	7	02-Apr-2024	0%	11	0	2
	Sources ingestion task	Python	23-Mar-2024	2	25-Mar-2024		3	0	2
	download excel/csv files	Python				0%
	extracting and preprocessing	Numpy & Pandas				0%
	Parsing landslide event data	Python	25-Mar-2024	5	29-Mar-2024		5	0	5
	import to PostgreSQL	Python				0%
	push coordinates value	Python				0%
	Weather data collecting	Python	27-Mar-2024	5	02-Apr-2024		7	0	5
	pull Coordinates value	Python				0%
	call REST API requests	Python				0%
	import to PostgreSQL	Python				0%
	Milestone 2

	Data mining	Apache Airflow	03-Apr-2024	16	24-Apr-2024	0%	22	0	10
	Statistical Analysis	Apache Spark	03-Apr-2024	10	16-Apr-2024		14	0	10
	Descriptive Analysis	Apache Spark				0%
	Inferential Analysis	Apache Spark				0%
	Causal Analysis	Apache Spark				0%
	Visualization	Nginx Webserver	17-Apr-2024	6	24-Apr-2024		8	0	6
	Chart & Graphs	ChartJS				0%
	Geo Map					0%
	Milestone 3

	Training model	Mlflow	25-Apr-2024	2	26-Apr-2024	0%	2	0	2
	Load data	Apache Spark	25-Apr-2024	2	26-Apr-2024		2	0	2
	normalization	Apache Spark				0%
	standardization	Apache Spark				0%
	choosing model	Mlflow
	Training	Mlflow	26-Apr-2024	1	26-Apr-2024		1	0	1
	tuning hyper parameter	Mlflow				0%
	monitoring	Mlflow				0%
	Milestone 4

	Triggering	Mlflow	25-Apr-2024	4	30-Apr-2024	0%	6	0	2
	Edge Device	Raspberry Pi 3	25-Apr-2024	2	26-Apr-2024		2	0	2
	GPS location	GPS module				0%
	Publish to MQTT broker	AWS IoT Core				0%
	Scheduling	Cron job				0%
	Inference	Python	26-Apr-2024	2	29-Apr-2024		4	0	2
	Subcribe to MQTT broker	Python				0%
	call REST API requests	Python				0%
	parse to model	Python				0%
	Visualization	Python	30-Apr-2024	1	30-Apr-2024		1	0	1
	Geo Map	Nginx Webserver				0%
	Alert mechanism
	Milestone 5

	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		1/1/14
		3/4/14
		4/18/14
		4/20/14
		4/25/14
		5/1/14
		6/10/14
		8/15/14
		12/8/14
		12/25/14